## test
Company : | JCS Consulting Inc
WBS Name | AppleSow 3
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Plug-ins |  |  | FILL IN HOURS |  |  | No
| Add-ons |  |  | FILL IN HOURS |  |  | No
| Custom HTML |  |  | FILL IN HOURS |  |  | No
| Custom Tiles |  |  | FILL IN HOURS |  |  | Yes
| Migrate Status Updates |  |  | FILL IN HOURS |  |  | Yes
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Configure Metadata and Attribute Mapping with SAML 2.0 Client |  |  | 5 |  |  | No
| Configure SAML 2.0 Client |  |  | 20 |  |  | No
| Create Custom SSO Plug-in |  |  | 60 |  |  | No
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Migrate Users |  |  | 10 |  |  | No
| Migrate Places |  |  | 10 |  |  | No
| Migrate Jive Documents |  |  | 10 |  |  | No
| Migrate Uploaded Documents |  |  | 10 |  |  | No
| Migrate Discussions |  |  | 20 |  |  | No
| Migrate Questions |  |  | 20 |  |  | No
| Migrate Ideas |  |  | 20 |  |  | No
| Migrate Polls |  |  | 20 |  |  | No
| Migrate Projects |  |  | 10 |  |  | No
| Migrate Task |  |  | 10 |  |  | No
| Migrate Blogs / Blogpost |  |  | 20 |  |  | No
| Migrate Bookmarks |  |  | 10 |  |  | No
| Migrate Events |  |  | 25 |  |  | No
| Migrate Videos |  |  | 25 |  |  | No
| Migrate Ratings |  |  | 10 |  |  | No
| Migrate Likes |  |  | 10 |  |  | No
| Migrate @ mentions |  |  | 30 |  |  | No
| Migrate Categories |  |  | 10 |  |  | No
| Migrate Status Updates |  |  | 20 |  |  | No
| Customization Plug-ins for Legacy Jive Instances |  |  | 60 |  |  | No
| Initial Data Load Sample |  |  | 40 |  |  | No
| QA / Bug Fixes (10 hrs per content type) |  |  | 60 |  |  | No
| Dry Run |  |  | 20 |  |  | No
| QA / Bug Fixes |  |  | 40 |  |  | No
| Go Live |  |  | 40 |  |  | No
| Fix Corrupt Data |  |  | 40 |  |  | No
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Log cases with Jive |  |  | 15 |  |  | No
| Dry Run #1 |  |  | 15 |  |  | No
| QA/ Bug Fixes |  |  | 15 |  |  | No
| Dry Run #2 |  |  | 15 |  |  | No
| QA/ Bug Fixes |  |  | 10 |  |  | No
| Go Live |  |  | 20 |  |  | No
| Post Upgrade Support |  |  | 15 |  |  | No
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Configure Code for Customer Instance |  |  | 15 |  |  | No
| Up to 15 hours to install and configure on Sandbox and Prod |  |  | 15 |  |  | No
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Custom Development Assesment |  |  | 10 |  |  | No
| Gamification Strategy |  |  | 5 |  |  | No
| Upgrade Strategy / Assesment |  |  | 20 |  |  | No
| SEO Strategy |  |  | 5 |  |  | No
| On Site (2 people/ 1 day) |  |  | 20 |  |  | No
| Community Plan |  |  | 10 |  |  | No
| Travel (2 people) |  |  | 50 |  |  | No
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Configure Nitro Console |  |  | 10 |  |  | No
| Configure Rewards Console |  |  | 25 |  |  | No
| Gamification Point Economy Plan |  |  | 20 |  |  | No
| Custom Bunchball Mission (per mission) |  |  | 4 |  |  | No
| Custom Quest (Rewards) |  |  | 2 |  |  | No
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Configure Code for Customer Instance |  |  | 15 |  |  | No
| Up to 15 hours to install and configure on Sandbox and Prod |  |  | 15 |  |  | No
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Custom Development Training |  |  | 10 |  |  | No
| Custom Development Documentation |  |  | 5 |  |  | No
| Gamification Training |  |  | 5 |  |  | No
| Admin Console Training (Per Session) |  |  | 3 |  |  | No
| Champion Training (Per Session) |  |  | 3 |  |  | No
| End User Training (Per Session) |  |  | 3 |  |  | No
| Group Admin Training (Per Session) |  |  | 3 |  |  | No
| Populate Help Center Content |  |  | 10 |  |  | No
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Site Design (3 Initial Proposals/3 Iterations on one Proposal) |  |  | 60 |  |  | No
| Wire Frames |  |  | 10 |  |  | No
| Cloud Theme |  |  | 10 |  |  | No
| Hosted / On Prem Theme (Per Theme) |  |  | 40 |  |  | No
| SEO Theme Customization |  |  | 20 |  |  | No
| Custom Desing Work |  |  | TBD |  |  | No