## test
Company : | JCS Consulting Inc
WBS Name | test
sso
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Configure Metadata and Attribute Mapping with SAML 2.0 Client | 233 |  | 5 |  | 1165 | No
| Configure SAML 2.0 Client | 233 |  | 20 |  | 4660 | Yes
| Create Custom SSO Plug-in | 233 |  | 60 |  | 13980 | Yes
Data Migration From Jive to Jive (Per 25000 pices of content)
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Migrate Users | 233 |  | 10 |  | 2330 | No
| Migrate Places | 233 |  | 10 |  | 2330 | No
| Migrate Jive Documents | 233 |  | 10 |  | 2330 | No
| Migrate Uploaded Documents | 233 |  | 10 |  | 2330 | No
| Migrate Discussions | 233 |  | 20 |  | 4660 | No
| Migrate Questions | 233 |  | 20 |  | 4660 | No
| Migrate Ideas | 233 |  | 20 |  | 4660 | No
| Migrate Polls | 233 |  | 20 |  | 4660 | No
| Migrate Projects | 233 |  | 10 |  | 2330 | No
| Migrate Task | 233 |  | 10 |  | 2330 | No
| Migrate Blogs / Blogpost | 233 |  | 20 |  | 4660 | No
| Migrate Bookmarks | 233 |  | 10 |  | 2330 | No
| Migrate Events | 233 |  | 25 |  | 5825 | No
| Migrate Videos | 233 |  | 25 |  | 5825 | No
| Migrate Ratings | 233 |  | 10 |  | 2330 | No
| Migrate Likes | 233 |  | 10 |  | 2330 | No
| Migrate @ mentions | 233 |  | 30 |  | 6990 | No
| Migrate Categories | 233 |  | 10 |  | 2330 | No
| Migrate Status Updates | 233 |  | 20 |  | 4660 | No
| Customization Plug-ins for Legacy Jive Instances | 233 |  | 60 |  | 13980 | No
| Initial Data Load Sample | 233 |  | 40 |  | 9320 | No
| QA / Bug Fixes (10 hrs per content type) | 233 |  | 60 |  | 13980 | No
| Dry Run | 233 |  | 20 |  | 4660 | No
| QA / Bug Fixes | 233 |  | 40 |  | 9320 | No
| Go Live | 233 |  | 40 |  | 9320 | No
| Fix Corrupt Data | 233 |  | 40 |  | 9320 | No
Upgrade
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Log cases with Jive | 233 |  | 15 |  | 3495 | No
| Dry Run #1 | 233 |  | 15 |  | 3495 | No
| QA/ Bug Fixes | 233 |  | 15 |  | 3495 | No
| Dry Run #2 | 233 |  | 15 |  | 3495 | No
| QA/ Bug Fixes | 233 |  | 10 |  | 2330 | No
| Go Live | 233 |  | 20 |  | 4660 | No
| Post Upgrade Support | 233 |  | 15 |  | 3495 | No
Customizations
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Plug-ins | 233 |  | FILL IN HOURS |  | nan | No
| Add-ons | 233 |  | FILL IN HOURS |  | nan | No
| Custom HTML | 233 |  | FILL IN HOURS |  | nan | No
| Custom Tiles | 233 |  | FILL IN HOURS |  | nan | No
| Migrate Status Updates | 233 |  | FILL IN HOURS |  | nan | No
Box for ServiceNow
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Configure Code for Customer Instance | 233 |  | 15 |  | 3495 | No
| Up to 15 hours to install and configure on Sandbox and Prod | 233 |  | 15 |  | 3495 | No
Strategy
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Custom Development Assesment | 233 |  | 10 |  | 2330 | No
| Gamification Strategy | 233 |  | 5 |  | 1165 | No
| Upgrade Strategy / Assesment | 233 |  | 20 |  | 4660 | No
| SEO Strategy | 233 |  | 5 |  | 1165 | No
| On Site (2 people/ 1 day) | 233 |  | 20 |  | 4660 | No
| Community Plan | 233 |  | 10 |  | 2330 | No
| Travel (2 people) | 233 |  | 50 |  | 11650 | No
Gamification
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Configure Nitro Console | 233 |  | 10 |  | 2330 | No
| Configure Rewards Console | 233 |  | 25 |  | 5825 | No
| Gamification Point Economy Plan | 233 |  | 20 |  | 4660 | No
| Custom Bunchball Mission (per mission) | 233 |  | 4 |  | 932 | No
| Custom Quest (Rewards) | 233 |  | 2 |  | 466 | No
Box for SFDC
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Configure Code for Customer Instance | 233 |  | 15 |  | 3495 | No
| Up to 15 hours to install and configure on Sandbox and Prod | 233 |  | 15 |  | 3495 | No
Training / Documentation
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Custom Development Training | 233 |  | 10 |  | 2330 | No
| Custom Development Documentation | 233 |  | 5 |  | 1165 | No
| Gamification Training | 233 |  | 5 |  | 1165 | No
| Admin Console Training (Per Session) | 233 |  | 3 |  | 699 | No
| Champion Training (Per Session) | 233 |  | 3 |  | 699 | No
| End User Training (Per Session) | 233 |  | 3 |  | 699 | No
| Group Admin Training (Per Session) | 233 |  | 3 |  | 699 | No
| Populate Help Center Content | 233 |  | 10 |  | 2330 | No
Training / Documentation
Line item | Task | Average Hourly Rate
|  |  | Low Hours | High Hours | Low Cost | High Cost | In Scope
| Site Design (3 Initial Proposals/3 Iterations on one Proposal) | 233 |  | 60 |  | 13980 | No
| Wire Frames | 233 |  | 10 |  | 2330 | No
| Cloud Theme | 233 |  | 10 |  | 2330 | No
| Hosted / On Prem Theme (Per Theme) | 233 |  | 40 |  | 9320 | No
| SEO Theme Customization | 233 |  | 20 |  | 4660 | No
| Custom Desing Work | 233 |  | TBD |  | nan | No