## Excel Test
No | Configure Metadata and Attribute Mapping with SAML 2.0 Client | 5
No | Configure SAML 2.0 Client | 20
Yes | Create Custom SSO Plug-in | 60
Hours | In Scope | Task
No | Migrate Users | 10
No | Migrate Places | 10
No | Migrate Jive Documents | 10
Yes | Migrate Uploaded Documents | 10
Yes | Migrate Discussions | 20
Yes | Migrate Questions | 20
No | Migrate Ideas | 20
No | Migrate Polls | 20
No | Migrate Projects | 10
No | Migrate Task | 10
No | Migrate Blogs / Blogpost | 20
No | Migrate Bookmarks | 10
No | Migrate Events | 25
No | Migrate Videos | 25
No | Migrate Ratings | 10
No | Migrate Likes | 10
No | Migrate @ mentions | 30
No | Migrate Categories | 10
No | Migrate Status Updates | 20
No | Customization Plug-ins for Legacy Jive Instances | 60
No | Initial Data Load Sample | 40
No | QA / Bug Fixes (10 hrs per content type) | 60
No | Dry Run | 20
Hours | In Scope | Task
No | Go Live | 40
No | Fix Corrupt Data | 40