## test
Company : | JCS Consulting Inc
WBS Name | Alans Bike shop - SOW 01 - Upgrade
Sso
Line item | Task | Average Hourly Rate
|  |  | High Hours | High Cost | In Scope
| Configure Metadata and Attribute Mapping with SAML 2.0 Client | 23 | 5 | 115 | Yes
| Configure SAML 2.0 Client | 23 | 20 | 460 | Yes
| Create Custom SSO Plug-in | 23 | 60 | 1380 | No
Data migration from jive to jive (per 25000 pices of content)
Line item | Task | Average Hourly Rate
|  |  | High Hours | High Cost | In Scope
| Migrate Users | 23 | 10 | 230 | Yes
| Migrate Places | 23 | 10 | 230 | Yes
| Migrate Jive Documents | 23 | 10 | 230 | Yes
| Migrate Uploaded Documents | 23 | 10 | 230 | Yes
| Migrate Discussions | 23 | 20 | 460 | Yes
| Migrate Questions | 23 | 20 | 460 | Yes
| Migrate Ideas | 23 | 20 | 460 | Yes
| Migrate Polls | 23 | 20 | 460 | Yes
| Migrate Projects | 23 | 10 | 230 | Yes
| Migrate Task | 23 | 10 | 230 | Yes
| Migrate Blogs / Blogpost | 23 | 20 | 460 | Yes
| Migrate Bookmarks | 23 | 10 | 230 | Yes
| Migrate Events | 23 | 25 | 575 | Yes
| Migrate Videos | 23 | 25 | 575 | Yes
| Migrate Ratings | 23 | 10 | 230 | Yes
| Migrate Likes | 23 | 10 | 230 | Yes
| Migrate @ mentions | 23 | 30 | 690 | Yes
| Migrate Categories | 23 | 10 | 230 | Yes
| Migrate Status Updates | 23 | 20 | 460 | Yes
| Customization Plug-ins for Legacy Jive Instances | 23 | 60 | 1380 | Yes
| Initial Data Load Sample | 23 | 40 | 920 | Yes
| QA / Bug Fixes (10 hrs per content type) | 23 | 60 | 1380 | Yes
| Dry Run | 23 | 20 | 460 | Yes
| QA / Bug Fixes | 23 | 40 | 920 | Yes
| Go Live | 23 | 40 | 920 | Yes
| Fix Corrupt Data | 23 | 40 | 920 | Yes
Strategy
Line item | Task | Average Hourly Rate
|  |  | High Hours | High Cost | In Scope
| Custom Development Assesment | 23 | 10 | 230 | Yes
| Gamification Strategy | 23 | 5 | 115 | Yes
| Upgrade Strategy / Assesment | 23 | 20 | 460 | Yes
| SEO Strategy | 23 | 5 | 115 | Yes
| On Site (2 people/ 1 day) | 23 | 20 | 460 | Yes
| Community Plan | 23 | 10 | 230 | Yes
| Travel (2 people) | 23 | 50 | 1150 | Yes
Upgrade
Line item | Task | Average Hourly Rate
|  |  | High Hours | High Cost | In Scope
| Log cases with Jive | 23 | 15 | 345 | No
| Dry Run #1 | 23 | 15 | 345 | No
| QA/ Bug Fixes | 23 | 15 | 345 | No
| Dry Run #2 | 23 | 15 | 345 | No
| QA/ Bug Fixes | 23 | 10 | 230 | No
| Go Live | 23 | 20 | 460 | No
| Post Upgrade Support | 23 | 15 | 345 | No
Customizations
Line item | Task | Average Hourly Rate
|  |  | High Hours | High Cost | In Scope
| Plug-ins | 23 | FILL IN HOURS | nan | No
| Add-ons | 23 | FILL IN HOURS | nan | No
| Custom HTML | 23 | FILL IN HOURS | nan | No
| Custom Tiles | 23 | FILL IN HOURS | nan | No
| Migrate Status Updates | 23 | FILL IN HOURS | nan | No
Box for servicenow
Line item | Task | Average Hourly Rate
|  |  | High Hours | High Cost | In Scope
| Configure Code for Customer Instance | 23 | 15 | 345 | No
| Up to 15 hours to install and configure on Sandbox and Prod | 23 | 15 | 345 | No
Gamification
Line item | Task | Average Hourly Rate
|  |  | High Hours | High Cost | In Scope
| Configure Nitro Console | 23 | 10 | 230 | No
| Configure Rewards Console | 23 | 25 | 575 | No
| Gamification Point Economy Plan | 23 | 20 | 460 | No
| Custom Bunchball Mission (per mission) | 23 | 4 | 92 | No
| Custom Quest (Rewards) | 23 | 2 | 46 | No
Box for sfdc
Line item | Task | Average Hourly Rate
|  |  | High Hours | High Cost | In Scope
| Configure Code for Customer Instance | 23 | 15 | 345 | No
| Up to 15 hours to install and configure on Sandbox and Prod | 23 | 15 | 345 | No
Training / documentation
Line item | Task | Average Hourly Rate
|  |  | High Hours | High Cost | In Scope
| Custom Development Training | 23 | 10 | 230 | No
| Custom Development Documentation | 23 | 5 | 115 | No
| Gamification Training | 23 | 5 | 115 | No
| Admin Console Training (Per Session) | 23 | 3 | 69 | No
| Champion Training (Per Session) | 23 | 3 | 69 | No
| End User Training (Per Session) | 23 | 3 | 69 | No
| Group Admin Training (Per Session) | 23 | 3 | 69 | No
| Populate Help Center Content | 23 | 10 | 230 | No
Training / documentation
Line item | Task | Average Hourly Rate
|  |  | High Hours | High Cost | In Scope
| Site Design (3 Initial Proposals/3 Iterations on one Proposal) | 23 | 60 | 1380 | No
| Wire Frames | 23 | 10 | 230 | No
| Cloud Theme | 23 | 10 | 230 | No
| Hosted / On Prem Theme (Per Theme) | 23 | 40 | 920 | No
| SEO Theme Customization | 23 | 20 | 460 | No
| Custom Desing Work | 23 | TBD | nan | No