## test
Company : | Jcs Consulting Inc,
WBS Name
In Scope | Hours | Task
No | FILL IN HOURS | Plug-ins
No | FILL IN HOURS | Add-ons
No | FILL IN HOURS | Custom HTML
Yes | FILL IN HOURS | Custom Tiles
Yes | FILL IN HOURS | Migrate Status Updates
sso
In Scope | Hours | Task
No | 5 | Configure Metadata and Attribute Mapping with SAML 2.0 Client
No | 20 | Configure SAML 2.0 Client
No | 60 | Create Custom SSO Plug-in
Data Migration From Jive to Jive (Per 25000 pices of content)
In Scope | Hours | Task
No | 10 | Migrate Users
No | 10 | Migrate Places
No | 10 | Migrate Jive Documents
No | 10 | Migrate Uploaded Documents
No | 20 | Migrate Discussions
No | 20 | Migrate Questions
No | 20 | Migrate Ideas
No | 20 | Migrate Polls
No | 10 | Migrate Projects
No | 10 | Migrate Task
No | 20 | Migrate Blogs / Blogpost
No | 10 | Migrate Bookmarks
No | 25 | Migrate Events
No | 25 | Migrate Videos
No | 10 | Migrate Ratings
No | 10 | Migrate Likes
No | 30 | Migrate @ mentions
No | 10 | Migrate Categories
No | 20 | Migrate Status Updates
No | 60 | Customization Plug-ins for Legacy Jive Instances
No | 40 | Initial Data Load Sample
No | 60 | QA / Bug Fixes (10 hrs per content type)
No | 20 | Dry Run
No | 40 | QA / Bug Fixes
No | 40 | Go Live
No | 40 | Fix Corrupt Data
Upgrade
In Scope | Hours | Task
No | 15 | Log cases with Jive
No | 15 | Dry Run #1
No | 15 | QA/ Bug Fixes
No | 15 | Dry Run #2
No | 10 | QA/ Bug Fixes
No | 20 | Go Live
No | 15 | Post Upgrade Support
Box for ServiceNow
In Scope | Hours | Task
No | 15 | Configure Code for Customer Instance
No | 15 | Up to 15 hours to install and configure on Sandbox and Prod
Strategy
In Scope | Hours | Task
No | 10 | Custom Development Assesment
No | 5 | Gamification Strategy
No | 20 | Upgrade Strategy / Assesment
No | 5 | SEO Strategy
No | 20 | On Site (2 people/ 1 day)
No | 10 | Community Plan
No | 50 | Travel (2 people)
Gamification
In Scope | Hours | Task
No | 10 | Configure Nitro Console
No | 25 | Configure Rewards Console
No | 20 | Gamification Point Economy Plan
No | 4 | Custom Bunchball Mission (per mission)
No | 2 | Custom Quest (Rewards)
Box for SFDC
In Scope | Hours | Task
No | 15 | Configure Code for Customer Instance
No | 15 | Up to 15 hours to install and configure on Sandbox and Prod
Training / Documentation
In Scope | Hours | Task
No | 10 | Custom Development Training
No | 5 | Custom Development Documentation
No | 5 | Gamification Training
No | 3 | Admin Console Training (Per Session)
No | 3 | Champion Training (Per Session)
No | 3 | End User Training (Per Session)
No | 3 | Group Admin Training (Per Session)
No | 10 | Populate Help Center Content
Training / Documentation
In Scope | Hours | Task
No | 60 | Site Design (3 Initial Proposals/3 Iterations on one Proposal)
No | 10 | Wire Frames
No | 10 | Cloud Theme
No | 40 | Hosted / On Prem Theme (Per Theme)
No | 20 | SEO Theme Customization
No | TBD | Custom Desing Work